## How to Use this Tool
Give BIG Green Bay - Marketing Tool
This tool is designed to help your organization plan, promote, and execute a successful giving day campaign. It is divided into four tabs—Save the Date, Get Ready to Give, Give TODAY, and Post-Giving Day—to guide you through every stage of your campaign. Each tab is fully customizable to fit your organization’s unique needs and goals: - Delete rows that don’t apply to your campaign - Add new rows for actions specific to your strategy, such as peer-to-peer fundraising Look to the sample entries as a guide and inspiration for your own ideas!
Follow these steps to make the most of it:
1. Navigate the phases
Each tab corresponds to a specific phase of the campaign. Start with the "Save the Date" tab to plan early outreach, then move to later phases as the campaign progresses.
Plan and Populate Each Tab:
For each phase, use the rows to categorize your outreach efforts by channel (e.g., Social Media, Email, Mailer, etc). Fill in the columns to organize your work:
Task: Identify the specific action needed (e.g., "Add a web banner to homepage," "Write a blog post").
Objective: Define the purpose or goal of the communication (e.g., "Increase visibility of our participation").
Message: Write the actual content or copy you plan to use (e.g., "We’re thrilled to announce our participation in #GiveBIGGB! Stay tuned for updates!").
Timing: Specify when you’ll complete or send the communication (e.g., "Jan 15" or "Week of Jan 14").
Platform: Indicate where the message will appear (e.g., Facebook, email, web page).
Assigned To: Delegate the task to a team member.
Status: Track progress (e.g., Not Started, In Progress, Completed).
Notes: Add reminders, tips, or special instructions.

## Save the Date
Phase I - Save the Date, January 13 - Feb 11
| Task | Objective | Message | Timing | Channel(s) | Assigned To | Status | Notes
Social Media | Post to all profiles | Announce participation | Check out Sample Social Posts for ideas! | Jan 13 (any time after 11:30AM) | FB, Insta, LinkedIn | Name | Not Started | Check out graphics to use or customize from the Nonprofit Toolkit
Email
Website | Add GBGB logo or banner | Link to campaign page
Mailer | [7 empty] | This could be a letter, postcard, newsletter, etc. Start planning now to ensure deliver prior to giving day.
Events | Meet w/ team to discuss | Determine whether to host one | What would the purpose be? | Decision by XX/XX
Other | [7 empty] | This could be handwritten notes, calls, text messages, or media interviews

## Get Ready to Give
Phase II - Get Ready to Give, Feb 11 - 24
| Task | Objective | Message | Timing | Channel(s) | Assigned To | Status | Notes
Social Media
Email | Email past donors | 2 Weeks Out Reminder | Explore sample email templates! | 2 weeks prior to GBGB | MailChimp |  | In process | Why support our campaign? When should they give?
Website
Mailer
Events
Other | Board Engagement |  | Find ideas to engage your Board members here!

## Give Today
Instructions for using this tab:
The Give TODAY tab is designed to help you manage and execute your communications and activities during the 24 hours of Give BIG Green Bay. It breaks the day into manageable time chunks, allowing you to plan and coordinate your efforts effectively. Steps to using this tool: 1. Add and customize blocks of time, communication channels, and columns to suit your organization's specific needs and goals. 2. Identify peak times for donor engagement (e.g., lunch breaks, evening hours) and plan targeted communications for these windows. 3. Stay flexible. Be prepared to adapt your schedule based on real-time results or unexpected opportunities.
Phase III - Give TODAY, Feb 25 & 26, noon-noon
| Task | Objective | Message | Timing | Channel(s) | Assigned To | Status | Notes
Enter chose timeframe here (i.e. 2/19, 12PM Hour)
Social Media |  |  | It's time to GIVE! Visit [insert link] to support our campaign. Every dollar donated will go further to make a greater impact. #giveBIGgb |  |  |  | Scheduled
Email | E-Blast | Give TODAY |  | 12:00
Website | Blog post | Ways to engage |  |  | Online
Events
Other | Media Opp | Awareness | Tell our story/Invite people to support | 12:15 | TV |  |  | Arrive 15 minutes early
Enter chosen timeframe here
Social Media | Facebook Live |  | Talk about where we're at
Email | E-Blast | Share a story
Website
Events | Open house | Engage community |  |  | Location:
Other
**Copy & paste additional blocks of time as needed

## Post-Giving Day
Phase IV - Post Giving Day Stewardship
| Task | Objective | Message | Timing | Channel(s) | Assigned To | Status | Notes
Social Media
Email | Email Donors | Thank you / Let's keep in touch | [5 empty] | Make sure to thank your donors, volunteers, staff, partners, peer-to-peer champions, and Board members
Website | Post Press Release
Mailer
Events | Team potluck | [6 empty] | Celebrate and review results!
Other | Press Release |  | Example: Share $ campaign results; Announce what the donations will be used for